## Slide 1
TOUR CONCEPT DECK · WORKING DRAFT
DETTY
DECEMBER
Fourteen titleholders and public figures, three countries, one December.
26 DECEMBER – 10 JANUARY (estimative)
CÔTE D'IVOIRE
GHANA
NIGERIA
Notes: Working draft. Concept is not yet signed off — see slide 2. Nothing in this deck should go to sponsors or talent until the flags on slide 8 are resolved.

## Slide 2
WHERE WE ACTUALLY ARE
The concept is not yet locked
Everything below the line needs answering with Olivia before this deck goes anywhere near a sponsor or a talent call.
ESTABLISHED
Three host countries — Côte d'Ivoire, Ghana, Nigeria
Arrival in Abidjan 26 Dec; Mother Africa Festival 27–28 Dec is the opening anchor
Roughly 26 Dec – 10 Jan, ending in Nigeria
All-female lineup of titleholders and public figures
A social-impact / foundation action in each country
Private jet air legs, vans and Escalades on the ground
No plus-ones — talent travel solo
Individual calls with each woman before anything is signed
OPEN — DECIDE WITH OLIVIA
The core purpose — celebration, tourism promotion, philanthropy, or a commercial content property?
Whose trip is this — Olivia and Dorcas's initiative we execute, or our concept they host?
What “Minister of Enjoyment” means in practice: curation, sign-off, public fronting?
Who funds it, and is our fee flat or tied to sponsorship?
Is the foundation piece core identity or a secondary activation?
Ghana cities and dates — the one fully open leg
Does NYE land in Abidjan or Lagos?
Is this a documented trip, or a media property that travels?
Until the left column and the right column agree, the itinerary, the sponsor deck and the talent contracts are all built on an assumption.
Notes: This is the slide to open the Olivia call with. Do not move to itinerary until the right column is answered.

## Slide 3
SHAPE OF THE TOUR
Route and approximate dates
Sixteen days, three countries, two confirmed anchors. Ghana is the open leg.
DEC 26
Arrival — Abidjan
Everyone lands. Rest day before the festival.
CONFIRMED
DEC 27–28
Mother Africa Festival
Marcory Zone 4. 4th edition, ~40,000 attendees. Olivia is already publicly linked to it.
CONFIRMED
DEC 29–31
Assinie · Sassandra · Yamoussoukro
Beach and heritage legs. Abidjan has a confirmed NYE fireworks anchor if NYE stays here.
DRAFT
EARLY JAN
Ghana
Cities and dates not yet chosen. Season runs under the government's “December in GH” programme.
OPEN
TO JAN 10
Lagos and Abuja
New Year's and a birthday. The most event-dense leg of the three.
DRAFT
Notes: Confirmed = date and venue are real and verified. Draft = we intend it but nothing is booked. Open = not yet decided at all.

## Slide 4
THE LINE-UP
Fourteen names on the list
On the list — not yet confirmed as attending. Reach figures are estimates from public sources, not media kits.
14
NAMES ON THE LIST
11 with a confirmed title
~6.1M
COMBINED INSTAGRAM REACH
estimated, unverified
~1.4M
COMBINED TIKTOK REACH
where an account was found
11
NATIONALITIES & TERRITORIES
one still unidentified
Real engagement rate and audience demographics are not public on any platform. They live in each woman's private Insights dashboard — the only way to get them is to request her official media kit during the individual calls.
Notes: If a sponsor asks for demographic data, the honest answer is that we are collecting media kits — do not present estimated follower counts as analytics.

## Slide 5
THE LINE-UP · 1 OF 3
Who is on the list
Ordered by Instagram reach. Drop cleared photographs into the circles — do not use images we have not licensed.
ADD
PHOTO
Olivia Yacé
CÔTE D'IVOIRE
Miss Côte d'Ivoire 2021 · 4th RU, Miss Universe 2025
IG ~1M
TikTok ~934K · FB ~756K
VERIFY TITLE
ADD
PHOTO
Veena Praveenar Singh
THAILAND
Miss Universe Thailand 2025 · 1st RU, Miss Universe 2025
IG ~2M
TikTok active
CORRECTED
ADD
PHOTO
Isabella Menin
BRAZIL
Miss Grand International 2022
IG ~1.05M
No other platform found
CONFIRMED
ADD
PHOTO
Nadia Mejia
ECUADOR / USA
Miss Universe Ecuador 2025 · Miss California USA 2016
IG ~435K
TikTok ~125K
CORRECTED
ADD
PHOTO
Alicia Aylies
FRENCH GUIANA
Miss France 2017
IG ~423K
TikTok ~148K · FB ~78K
CONFIRMED
Follower figures are approximate, from public search — verify against each media kit before any of this reaches a sponsor.

## Slide 6
THE LINE-UP · 2 OF 3
Who is on the list
Ordered by Instagram reach. Drop cleared photographs into the circles — do not use images we have not licensed.
ADD
PHOTO
Angélique Angarni-Filopon
MARTINIQUE
Miss France 2025 — first Martinican winner
IG ~395K
No personal TikTok
CORRECTED
ADD
PHOTO
Rebecca Biangue
FRANCE
Beauty & lifestyle creator — no title found
IG ~220K
TikTok ~43K
NO TITLE
ADD
PHOTO
Dorcas Dienda
DR CONGO
Miss Africa 2019 · Miss Universe DR Congo 2025
IG ~216K
TikTok active
CONFIRMED
ADD
PHOTO
Ophély Mézino
GUADELOUPE
Miss World 2019 1st RU · Miss Universe Guadeloupe 2025
IG ~141K
TikTok ~35K · FB ~20K
CONFIRMED
ADD
PHOTO
Nellie Anjaratiana
MADAGASCAR
Miss Madagascar 2020 · Top 40, Miss World
IG ~80K
Facebook ~105K
CONFIRMED
Follower figures are approximate, from public search — verify against each media kit before any of this reaches a sponsor.

## Slide 7
THE LINE-UP · 3 OF 3
Who is on the list
Ordered by Instagram reach. Drop cleared photographs into the circles — do not use images we have not licensed.
ADD
PHOTO
Sephora Kongo
DR CONGO
Fashion & lifestyle influencer — no title found
IG ~73K
TikTok ~39K
NO TITLE
ADD
PHOTO
“Tai”
UNKNOWN
No name, nationality or credentials found
IG ~43–63K
No other platform found
UNIDENTIFIED
ADD
PHOTO
Khaiza Kuyo
CÔTE D'IVOIRE
Actress, Ivorian series “Isabelle” — no title found
IG ~33K
TikTok ~57K
NO TITLE
ADD
PHOTO
Bella Zabaneh
BELIZE
Miss Universe Belize 2025
IG ~23K
TikTok ~22K
CONFIRMED
Follower figures are approximate, from public search — verify against each media kit before any of this reaches a sponsor.

## Slide 8
BEFORE ANYTHING IS SENT
Seven corrections to the original list
These came out of verifying every name against public record. Resolve them with whoever wrote the original notes.
1
Two titles were swapped
Veena Praveenar Singh is Miss Universe Thailand 2025 and 1st Runner-Up at Miss Universe 2025. Isabella Menin is Miss Grand International 2022. The original notes attached Isabella's title to Veena.
2
Three names have no pageant title
Khaiza Kuyo, Rebecca Biangue and Sephora Kongo return no title in public search — actress, content creator and influencer respectively. Not a reason to drop them; a reason to fix how they are described.
3
“Tai” is unidentified
An Instagram handle and nothing else — no name, nationality or credentials. Needs a direct answer from the source of the original note.
4
“+1 Angelique” is ambiguous
Either a second, different Angelique, or a stray reference back to Angélique Angarni-Filopon. Unresolved by research — do not guess.
5
Angélique's title year is wrong
Miss France 2025, not 2019. First Martinican winner and the oldest woman ever crowned — both worth using in promotion.
6
Olivia's affiliation changed
She resigned the Miss Universe Africa & Oceania title on 24 November 2025, keeping Miss Côte d'Ivoire. Confirm her status before any Miss Universe branded material.
7
Nadia Mejia is not the singer
This is Nadia Grace Eicher Mejía-Webb, Miss Universe Ecuador 2025 — not the Chilean singer of the same name, in case that was the intent.
Notes: Items 1-4 are blocking — nothing outbound until they are answered. Items 5-7 are factual corrections we can make ourselves.

## Slide 9
LEG ONE · 26–31 DECEMBER
Côte d'Ivoire
Abidjan, Assinie, Sassandra, Yamoussoukro. The strongest leg on paper — one confirmed anchor and an existing talent relationship.
EVENTS
Mother Africa Festival
27–28 Dec, Marcory Zone 4. ~40,000 attendees, 4th edition. Founder: Kimany Tayoro.
NYE fireworks
31 Dec, Général de Gaulle bridge over the Ebrié Lagoon. Free, city-wide, PM in attendance.
Sofitel Réveillon gala
31 Dec, Congress Palace. Past editions featured Magic System live.
Nahiko, Assinie
Smaller lagoon-side NYE dinner — the VIP alternative to Abidjan.
SPONSOR TARGETS
Orange Côte d'Ivoire
Runs a formal sponsorship programme — sponsors events as policy.
Air Côte d'Ivoire
AFCON 2023 official carrier; backed the Children of Africa gala via the First Lady's office.
Solibra
Ivorian since 1955, FEMUA sponsor history, marking its 70th anniversary.
Brassivoire
Heineken/CFAO joint venture, runs its own brand events in Abidjan.
PARTNERS & LOGISTICS
La Sunday
Abidjan's signature day-party brand, 6,000+ attendees on the lagoon.
Ivory Jet Services
New Abidjan base, European AOC, Falcon and Legacy aircraft. Matches the charter in the brief.
Sofitel · Radisson Blu · Hôtel Président
Assinie boutique: Nahiko, Maison d'Akoula, Key 19.
Monbolide · WINO · Auto Ivoire
Chauffeur fleets. Sedan ~55–70k FCFA/day, SUV ~80–120k.
WATCH
Grand-Bassam's beaches were closed on 30 December last year after an oil spill, reopening under restrictions from 1 January. If a Bassam beach day stays on the route, check live status before committing.

## Slide 10
LEG TWO · EARLY JANUARY
Ghana
Cities and dates still open. The whole season runs under a government programme — that is the fastest way in.
EVENTS
“December in GH”
Government programme, 1 Dec – 3 Jan, run by the Ghana Tourism Authority. Open call for event partners.
AfroFuture Fest
~27–29 Dec, El Wak Stadium. ~31,000 attendees. Run by Culture Management Group.
Detty Rave
~27 Dec, Untamed Empire. Mr Eazi's event — the biggest celebrity draw on the calendar.
Polo Beach Club NYE
31 Dec, Labadi. Tiers from ₵500 to ₵70,000 — a useful VIP pricing benchmark.
SPONSOR TARGETS
Ghana Tourism Authority
Runs the season and takes partner proposals. Also the route to Miss Diaspora Ghana.
MTN Ghana
Deep concert sponsorship history, plus a foundation — sponsor and impact partner in one.
AirtelTigo
First operator to launch eSIM in Ghana — direct fit for a connectivity deal.
Guinness Ghana · Kasapreko
Dominant beverage players. No confirmed festival tie-in — needs direct outreach.
PARTNERS & LOGISTICS
Culture Management Group
The most internationally professionalised producer in the market.
McDan Aviation
Ghana's dominant private-jet terminal at Kotoka. 2025 Aviation Company of the Year.
Kempinski · Labadi Beach · Mövenpick
The standard luxury shortlist for high-end Accra groups.
SOS Children's Villages Ghana
11 locations since 1974 — the most credible foundation partner found.
WATCH
No 2026 dates are published yet for AfroFuture, Detty Rave, Afro Nation or the December concerts — they typically drop in September and October. Everything above is last season's pattern. Cape Coast is confirmed weak for December nightlife: treat it as a daytime heritage stop only.

## Slide 11
LEG THREE · NEW YEAR TO 10 JANUARY
Nigeria
Lagos and Abuja. The most event-dense leg, and the only one with confirmed active sponsors in the space.
EVENTS
Flytime Fest
21–25 Dec, Eko Convention Centre. 21 years running; Davido closed the 2025 edition.
Livespot Detty December Fest
6–31 Dec. Co-produced with the Federal Ministry of Arts and Culture.
Abuja Groovy December
15–31 Dec, Moshood Abiola Stadium. Includes a “Miss Groovy December” pageant.
Transcorp Hilton Abuja
Runs its own NYE gala and a New Year's Day show — a turnkey Abuja venue partner.
SPONSOR TARGETS
Wema Bank (ALAT)
Confirmed headline Detty December sponsor last season; also backed Davido's tour.
Martell · Guinness · Hennessy
All three ran confirmed premium activations. Hennessy owns its own event property.
MTN · Airtel · Glo
Heavy festive-data marketing. No confirmed festival deal — strong pitch targets.
Eko Hotels & Suites
Runs its own December festival property; GM speaks publicly on Detty December.
PARTNERS & LOGISTICS
Livespot360
The dominant producer, government-endorsed, led by Deola Art Alade. Prior Cardi B booking.
ExecuJet Africa
Major FBO at Murtala Muhammed; hangar rated to Boeing Business Jet size.
Zeniks · Abuja Car Rental Express
Motorcade and escort options; armoured vehicles available in Abuja.
Wellbeing Foundation Africa
Founded by Toyin Ojora Saraki. Maternal and child health — pairs well with the birthday.
WATCH
Lagos State's own free New Year's flagship was cancelled hours before kickoff on 31 December last year, with no reason given, after running annually since 2012. Do not anchor the NYE plan on it until 2026 status is confirmed.

## Slide 12
THE DECISION THAT SIZES THE CREW
What kind of content is this
This changes crew, budget and timeline more than any other choice. It should be settled at concept stage, not once cameras are already on the ground.
A
Highlight reel
One videographer shooting coverage and behind-the-scenes, cut into a 3–5 minute recap with social versions after the trip.
Crew: 1–2 — matches the current sheet
+ Cheap, fast, low risk.
− Gives sponsors nothing sustained, and badly undersells the story.
B
Social-first + episodic
Daily short-form posted live for reach, same footage banked and cut into three long-form episodes — one per country — after the trip.
Crew: 1–2 videographers, photographer, on-trip editor, post editor
+ Content flows during the tour when sponsors need visibility, and still yields a polished asset.
− Needs a slightly bigger crew than currently budgeted.
RECOMMENDED
C
Full documentary series
Two episodes per country. A director, DP, sound, second camera, drone, colourist and story editor, with a narrative arc built in advance.
Crew: full production team + months of post
+ The most valuable long-term asset, and a genuinely strong story.
− A separate project with its own producer, budget and distribution plan. Not an add-on.
Recommendation: shoot at documentary quality — multi-camera on the big moments — but only commit to three episodes now. That keeps option C open later without having under-shot the first time.
Notes: Running a full reality-series production inside a 16-day, three-country, festival-hopping schedule with the crew currently on the sheet is the highest-risk path.

## Slide 13
WHAT THE ROLE ACTUALLY COVERS
Scope of work
The brief named logistics, sponsorship, itinerary, negotiation and oversight. At this scale the role is closer to executive producer — here is the rest of it.
NAMED IN THE BRIEF
Tour logistics
Sponsorship & partnership deals
Itinerary management
Negotiations with all parties
General tour oversight
TALENT & DUTY OF CARE
Talent contracts & appearance terms
Rider management across 14 women
Conflict resolution on the ground
Media kit collection & distribution
LEGAL & RISK
Waivers, insurance, medical cover
Filming & work permits per country
NDAs for sponsors and partners
Force majeure & cancellation terms
IMMIGRATION
Visa coordination, three countries
Passport collection & tracking
Documentation for private jet legs
SECURITY
Advance planning & route recon
Crisis communication protocol
Local law enforcement liaison
FINANCE
Master budget ownership
Multi-currency cash flow — CFA, Cedi, Naira
Vendor payment schedules & deposits
FOUNDATION PROGRAMME
NGO vetting per country
Gift & supply procurement
Consent for filming beneficiaries
Impact reporting for sponsors
CONTENT OPERATIONS
Posting calendar & platform strategy
Usage rights and ownership
Press and media-day management
WRAP-UP
Post-tour sponsor reporting deck
Talent payment reconciliation
Debrief and archive
Notes: Worth confirming which of these the client assumes is ours versus theirs — particularly security hire and foundation programme management.

## Slide 14
WHAT HAPPENS NEXT
Action steps
Four blocking items, then everything else can run in parallel.
BLOCKING — THIS WEEK
1
Confirm the concept with Olivia
Purpose, ownership, funding, and what “Minister of Enjoyment” means in practice.
2
Send the roster corrections
Title swap, three untitled names, “Tai”, and the “+1 Angelique” ambiguity.
3
Lock Ghana cities and dates
Hotels, sponsors and RSVPs there are all downstream of this.
4
Set the budget ceiling and paying client
Sponsor pitches and vendor talks cannot really start without it.
IN PARALLEL
Individual calls with each woman — concept, availability, terms
Collect handles, follower counts and official media kits
Passport and visa documentation as confirmations land
Olivia's local list: Mother Africa organiser, Bassam beach status, sponsor outreach, Côte d'Ivoire foundation partner
Apply into Ghana Tourism Authority's “December in GH” partner process
Confirm Lagos NYE flagship status for 2026
Decide the content production model and size the crew
Build sponsor decks once talent and route are locked
Confirm head of security plus two, begin advance planning
Nothing outbound — no sponsor deck, no talent email — until items 1 and 2 are answered.

## Slide 15
THE ONE THING TO SETTLE FIRST
What is this trip actually for?
Celebration, tourism promotion, philanthropy, or a commercial content property. They are not mutually exclusive — but one of them has to be the organising idea that the itinerary, the sponsors and the fourteen individual conversations are all built to serve.
Answer it with Olivia, and everything else in this deck becomes a scheduling problem.